## Sheet1
Notes |  | Who`s handling |  | Status | Priority |  | Tasks
| Scrum Master | Product Owner | Developers | Comments | 1-5
| Scrum Master |  | Developers |  | 3 | SubTasks | Define MVC model packages and the classes according to MVC .
build the three Model Packages
intiate Model / Controller/View Classes
|  |  | Developers |  | 4 | SubTasks | Initializing SysData class | מקרא צבעים
Enable reading and writing to JSON Files ( Questions )
implementing other functional methods
reading board files and converting to 2D Array
| Scrum Master |  | Developers |  | 4 | SubTasks | Build the Base Class of the Model Such as : Game , Question
implementing Timer - Stop Watch
implementing Tile Generator
implementing queen movments
[6 empty] | implementing soldier movments |  |  | הושלם ועבר אינטגרציה
|  | Product Owner |  |  | 5 | SubTasks | Initiate testing phase, define tests ,perform Junit tests to insure Code Quality, functionality, reusability and making error checks. |  | בטיפול
Test Stop Watch working properly
Test Queen Movments - Kill Moves
Test Queen Movments -Plain Moves
Test Turn Switching
Test Soldier Movments - Kill Moves
Test Soldier Movments -Plain Moves
| Scrum Master |  | Developers |  | 5 | SubTasks | Build the View layer by implementing all the GUI Classes such as : tile, soldier, queen, main page. |  | לא באיטרציה הנוכחית
View- implement Classes : Soldier,Queen
View- implement Classes : Tile
[5 empty] | 5 | SubTasks | Build the game board and implement its graphics, add game and turn timer.
Build GamePlay Screen & implement Board
impelment Turn Timer + Game Timer
[5 empty] | 4 | SubTasks | Build the graphic interface of the main menu, options screen, tutorial screen, game history screen and load game screen.
Build Main menu Screen
Build tutorial Screen
Build Load Screen
Build Game History
| Scrum Master |  |  |  | 3 | SubTasks | Add the ability to navigate between the screens we implemented earlier and add functionality to the screen contents(eg. turn on/off soundtrack).
link GUI Screens : Back Buttons , Navigation in General
[5 empty] | 5 | SubTasks | Implement the graphics of the soldier/queen(white/black stones), special tiles, point system and initialize them upon game start.
GamePlay Screen - implement functions : Soldier Movements
GamePlay Screen - implement functions : Queen Movements
GamePlayScreen - implement Colored Tiles in Board
| Scrum Master | Product Owner |  |  | 5 |  | Define and perform tests for the previous tasks.
Implement questions pop-ups and enable the player to select an answer.
Implement in-game notifications and messages.(eg. Player won, Game Finished, etc..)
Implement tutorials for the game that will demonstrate different scenarios.
Enable load/save game feature.
Test the performance and the functionality of the game and finalize the view of the game.